## Sprint1
Issue # | User Story/Tasks Issues | Description/Tasks Issues | Responsible | Priority | Risk | Due Date | Notes
1 | [US.01] Login Page | Task 1 Issue#12 Task 2 Issue#13 Task 3 Issue#14 | Abdulah, Botao, Gregory, James | High | Medium | 2024-09-29
2 | [US.02] Role dashboard | Task 1 Issue#15 Task 2 Issue#16 | Abdulah, Botao, Gregory | Medium | Low | 2024-09-29
3 | [US.03] Admin dashboard | Task 1 Issue#17 Task 2 Issue#18 | Abdulah, Jeremy, Tameera | Low | Low | 2024-09-30
12 | [US.01 Task 1] | Upon entering the website URL, the user should be presented with the login page as the first page | Botao, Gregory, James | High | Medium | 2024-09-26
13 | [US.01 Task 2] | Using the provided login credentials, the user is able to type their user/password and submit the login request | Abdulah, Gregory, James | High | High | 2024-09-27
14 | [US.01 Task 3] | User can login successfully if credentials match a valid credential in the database (MongoDB) | Abdulah | High | High | 2024-09-27
15 | [US.02 Task 1] | After successfully login request, professor accounts will be presented with the admin dashboard. | Abdulah, Botao, Gregory | Low | Low | 2024-09-27
16 | [US.02 Task 2] | After successfully login request, student accounts will be presented with the user dashboard. | Abdulah, Botao, Gregory | Low | Low | 2024-09-27
17 | [US.03 Task 1] | Professors (admins) should have a function to import a CSV file in order to load his class roaster. | Abdulah | Low | Medium | 2024-09-30
18 | [US.03 Task 2] | Professors (admins) will have access to creating/managing groups and assigning students to the groups | Jeremy, Tameera | Medium | Medium | 2024-09-30

## Sprint2
Issue # | User Story/Tasks Issues | Description/Tasks Issues | Responsible | Priority | Risk | Due Date | Notes
19 | [US.03 Task 3] | Professors (admins) will have access to a dashboard showcasing a list of all students with their average grading. |  | Idk | Idk
20 | [US.03 Task 4] | Professors (admins) will have a page to review the anonymous rating students have given him/her. |  | Idk | Idk
-